## Slide 1
Group 9
Event Logistics
Audi F1 team
Submitted to: Prof. Dr. Iris Hausladen
Nikhil Agarwal
Anamika Das
Shu Chen
Vrinda Mehra

## Slide 2
Executive summary
Challenge Overview The Audi F1 Team faces intense logistics demands, especially during back-to-back races like Japan (Apr 4–6), and Saudi Arabia (Apr 18–20), requiring rapid packing, shipping, and setup across 3 countries and 2 continents in just over 2 weeks.
Critical Risks
Time Constraints: Tight schedules risk delays in car readiness.
Customs Compliance: Varied protocols in China, Japan, Saudi Arabia, USA, and Brazil threaten equipment clearance.
Weather Disruptions: Fog, storms, and monsoons can delay urgent cargo.
Logistics Strategy
Categorized Shipping: Critical items (cars, IT gear) by air; non-critical items via sea in pre-shipped rotating sets.
Stakeholder Coordination: Team logistics, drivers, engineers, and partners (e.g., DHL) collaborate for seamless operations.
Outsourcing Focus: Prioritize global freight, trackside setup, and reverse logistics through ABC analysis.
Key to Success
Proactive planning, contingency strategies, and robust SLAs to mitigate risks and ensure compliance.
"Precision in logistics drives performance on the track."

## Slide 3
Introduction
Massive Movement, Tight Timelines
Formula 1 logistics is the high-speed, global operation that ensures every car, part, and person arrives at the right place, at the right time — across 20+ races, 5 continents, and just 9 months
1400+ tons of freight per person
Travel by air (for critical gear), sea (for non-critical cargo), and road
Only days to move everything between races
What’s Moved?
Global Planning & Coordination
Race cars, spare parts, IT racks, tools, garage setups
Crew equipment, media kits, hospitality units
Customs clearance, weather delays, and tight race calendars demand military-level precision
Some setups begin while another race is still ongoing
Efficient logistics are the foundation of every Grand Prix — without them, the race cannot begin, the cars cannot perform, and the show cannot go on.
Overview of logistics involved in Formula 1

## Slide 4
Global travel & tight schedule
Rapid Setup and Teardown
Weather disruptions
Customs and Regulations
High chance of forgetting Items
Parts are categorized - critical items travel by air, others by sea in multiple sets.
5 sets of non-critical items are sent in advance, rotating them between global races.
One missing tool or component can delay car readiness or compliance checks.
Races spanning China, Japan, Saudi Arabia, USA, and Brazil could bring unique customs protocols.
Audi must maintain compliance and have contingency strategies to avoid delays in equipment clearance.
Weather delays can disrupt transport
Fog in Mexico or storms in Florida can delay urgent air cargo, risking setup time.
High winds or closed tunnels can stop trucks or sea freight unexpectedly.
Tight timelines and long distances pose a major challenge.
Teams must shift from Japan to Bahrain to Saudi Arabia within 15 days.
Back-to-back races in Mexico, Brazil, Las Vegas, and Qatar could create complex air and sea freight coordination issues.
Key Challenges
Key Grand Prix Logistics Challenges for Audi F1 Team

## Slide 5
Complexity and Scale of Operations
F1 teams move around 1,500 tons of gear—cars, tools, and team equipment—across 20+ countries in one season. This requires careful planning and global coordination.
Time-Sensitive Scheduling
With races often held back-to-back, teams must pack, fly, and set up everything within days—like going from Las Vegas to Abu Dhabi in under a week.
Fan expectations & Media Pressure
A smooth operation boosts fan engagement, while any logistical hiccup is instantly broadcasted on social media, risking brand damage.
Environmental responsibility
The environmental impact of global logistics is a growing concern. F1 aims for net-zero carbon emissions by 2030, pushing for greener transport methods like biofuels.
Key Focus: Formula 1 Logistics
Role of Logistics in Sports Event Management
Technological and Logistical Precision
Transporting delicate and high-value equipment, such as cars and their components, demands meticulous handling. Teams need to ensure they arrive in optimal condition and are ready for competition.

## Slide 6
Categorical distribution of Potential Logistics Tasks through ABC Analysis
Potential Logistics Tasks for Outsourcing to LSPs
Global Freight & Customs Handling
Race Equipment Transportation
Trackside Setup & Dismantling
Last-Mile Urgent Deliveries
Reverse Logistics
Temporary Warehousing Nearby
Personal Travel & Accommodation
Sustainable Logistics Solutions
Catering & Hospitality Logistics
IT Equipment & Data Logistics
A
B
C

## Slide 7
Selecting the Best LSP for Audi F1 Logistics
Audi F1 requires a logistics partner capable of managing global, time-critical, and sustainability-driven operations across 20+ Grand Prix events.
International Transport (air/sea/road)
On-Site Race Logistics (setup, teardown, storage)
Customs Clearance & Documentation
Spare Parts & Equipment Handling
Reverse Logistics
Merchandise & Promo Logistics
Sustainability Consulting
Outsourced Tasks
The goal is to select a logistics partner who can deliver flawlessly, adapt under pressure, and contribute to Audi’s net-zero ambition.
To define the challenges and scope

## Slide 8
Inspect systems, CO₂ practices, real-time tracking
Task breakdown + internal interviews
Filter, compare offers, validate claims
LSP Selection Procedure: Step-by-Step Framework
Define Scope & Needs
Set Requirements & KPIs
Market Research & Longlist
RFI / RFP Rounds
Audit & Site Visits
Evaluation via Scoring Model
On-time delivery, sustainability, crisis readiness
Use Multi-Criteria Decision Analysis to quantify strengths
Global players + motorsport specialists
What’s the process to find the best?

## Slide 9
Multi-Criteria Decision Matrix (MCDA)
Criteria | Weight (%) | Why it matters
Sustainability (CO₂, circularity) | 20% | Audi F1’s green agenda
Delivery performance (OTD, lead time) | 15% | Can’t afford delays
Cost efficiency | 15% | Value over lowest price
Experience in motorsport | 15% | Speed, secrecy, reliability
Tech capabilities (API, tracking) | 10% | Real-time visibility
Crisis flexibility | 10% | Customs delays, rerouting
Reputation | 5% | References, case studies
Financial stability | 5% | No collapse mid-season
Innovation potential | 5% | Forward-looking partners
Chart: 
| Sustainability | Delivery performance | Cost efficiency | Experience in motorsport | Tech capabilities | Crisis flexibility | Reputation | Financial stability | Innovation potential
Weight | 20 | 15 | 15 | 15 | 10 | 10 | 5 | 5 | 5
We prioritize sustainability and F1-specific expertise over lowest-cost offers.
The metrics of evaluation model

## Slide 10
Streamline Success: Key Logistics Tasks to Outsource for Peak Performance
Strategic Partner Selection: Criteria for Logistics Excellence
Real-Time tracking availability
Scope: Full supply chain visibility (including in-transit location, ETA, customs status).
Justification: Essential for race preparation and agile response to disruptions.
Accuracy in Inventory & Order Fulfilment
Scope: Correct quantity, type, and condition of race-critical components delivered.
Justification: Miss deliveries (e.g., wrong tire compounds or tools) can jeopardize pit operations.
Damage-Free delivery
Scope: Correct quantity, type, and condition of race-critical components delivered
Justification: Miss deliveries (e.g., wrong tire compounds or tools) can jeopardize pit operations
On-time Delivery
Scope: Spare parts, race equipment, tools, gear, and sponsor materials Justification: A single delayed delivery can compromise race performance or violate regulations
Sustainability Compliance
Scope: Shipping, warehousing, last-mile delivery.
Justification: Audi F1’s no fossil fuel vision and circular economy commitment
Custom clearance efficiency
Scope: All cross-border freight for F1 events
Justification: Formula 1’s global circuit necessitates seamless cross-border movement
Issue resolution response time
Scope: Lost, or delayed goods; customs issue; incorrect deliveries.
Justification: Quick response time minimizes operational risks.

## Slide 11
SLAs That Deliver: Ensuring Excellence Through Rigorous Monitoring
KPI Dashboards - Real-time dashboard tracking using SLA metrics - Built on ICT systems (ERP/SCM integrated with IoT for asset tracking)
Penalty & Incentive Structure - Financial penalties for non-compliance (e.g., late deliveries) - Bonuses for exceeding benchmarks
Weekly performance Reports Automated reports highlighting compliance, deviations, and root causes
Site Audits & Spot Checks On-site verification of packaging, loading practices, and warehouse conditions at key locations
Regular Review Meetings Monthly or post-race review sessions with the LSP to evaluate performance and plan improvements
Feedback Loops Internal team feedback (e.g., race engineers, pit crew) on logistical sufficiency and performance
Service Level Agreements (SLAs) & Monitoring

## Slide 12
References
https://www.businessinsider.com/how-formula-one-team-transports-drivers-cars-staff-world-season-2023-11
https://www.grandprix247.com/2023/12/20/logistics-behind-f1-how-formula-one-moves-around-the-world/
https://www.freightwaves.com/news/the-extreme-logistics-behind-formula-ones-global-circus
https://f1destinations.com/the-logistics-of-formula-1/
https://www.crash.net/f1/news/1028168/1/mindblowing-logistics-how-f1-flies-20-hours-las-vegas-abu-dhabi
https://www.youtube.com/watch?v=IdzfJMyZTZU
https://www.youtube.com/watch?v=vFsHHuTtXC0
https://www.youtube.com/watch?v=6OLVFa8YRfM
https://www.youtube.com/watch?v=9DTpQ8LGE2c
https://www.youtube.com/watch?v=FYz5bxZJUgU

## Slide 13
Thank you